Additional Red Flags with Parameters

| Sl. | Audit Criteria | Source/Data which were used for analysis | Particulars of Division/ Work/ Voucher where red flag noticed | Steps implemented for red flag detection | Parameters required for red flag |
| --- | --- | --- | --- | --- | --- |
| 1 | Excess Expenditure than estimated quantity- As per Clause 38, tender quantities are approximate and no rate revision is permissible if the quantity variation is within 25% and the excess value beyond this limit does not exceed ₹ 5,000. | BEAMS Utilization Certificate | In PWD Nagpur-2, on work of Improvement to Tidgangi Dahera Rd- the total expenditure incurred on the work was ₹1.03 crore against the contract agreement amount of ₹ 0.75 crore, indicating excess expenditure of ₹28 lakh, (37 percent) over the contract cost. | BEAMS -> MIS -> PWD Works -> PWD Capital Works Report (Roads)->Utilisation certificate (in pdf)-> Expenditure Details-> RA Bills Detailed | If Cumulative Expenditure in Expenditure Details of Utilisation Certificate under work details under work id of PWD capital works- is in excess of Contract Cost by more than 25% then there is red flag for excess expenditure |
| 2 | Abandoned work- If there is no progress in execution of works for last 2-3 years and work is yet to be completed then a decision should be made regarding withdrawal of work or imposition of penalty on contractor | BEAMS-MIS- PWD Capital Works- Work details | In PWD Nagpur-2, in work of Construction of Cement Concrete Road and two Years Maintenance of on Hudkeshwar Matkazari Road in Nagpur Km. 3.0 to 8.00, expenditure of Rs. 12.52 crore was incurred against the contract cost of Rs. 17.80 crore. Only 70% fund is utilized and no payment after March 2021 was made indicating abandoned work | BEAMS -> MIS -> PWD Works -> PWD Capital Works Report (Roads)->Utilisation certificate (in pdf)-> Expenditure Details-> RA Bills Detailed | If Cumulative Expenditure in Expenditure Details of Utilisation Certificate under work details under work id of PWD capital works- is less than the Contract Cost by 25% and last RA bill paid is more than 3 years ago then there is red flag for Abandoned work |
| 3 | Inflated SSR/DSR- As per para 150 of MPW Manual, Estimates should be recast when accepted tender for a work is less than by 10 per cent of the estimated cost | Agreement Register | In PWD Nagpur-2, no. of awarded works which were accepted at rate below 10% of the estimated cost/ tendered cost was nearly 50% of the total awarded works during the year i.e. 315 out of 644 and cost of these works was 20.52 percent of total cost of all awarded works during the year | Agreement Register -> % above or Below column is filtered to find out no. of works accepted with tenders below 10% and contract cost of such works. Then percentage of no. of works as well as percentage of contract cost of such works against total works was calculated. | If no. of works accepted by the division is found out in excess of 20% of the total works in a year or cost of below tenders is more than 20% of the total awarded cost of all works during the year then it is a red flag for inflated SSR/DSR (State Schedule of Rates/ District Schedule of Rates) |
| 4 | Parking of fund- As per provisions of Budget Manual transfer of fund should not be | BEAMS-MIS- PWD Capital Works- Work details | In PWD Nagpur-2, fund of ₹ 1.80 crore was transferred to electrical division at the fag end of the year and the same work was found in Deposit Module, where the amount was received back from the Electric Division next year. | BEAMS -> MIS -> PWD Works -> PWD Capital Works Report (Building) ->Utilisation certificate (in pdf)-> Expenditure Details-> Transfer to Electrical division at the fag end of year | If in Expenditure Details under PWD Capital Works in BEAMS-MIS -> UC, there is Payment of huge amount (more than ₹ 50 lakh) to other division in month of March then there is red flag for parking of fund. |
| 5 | Non-recovery of damage charges or non-imposition of penalties for delayed execution of the work- If work is not completed by the contractor within the stipulated time then the contractor is liable to pay damages as stipulated in the agreement | BEAMS-MIS- PWD Capital Works- Work details | In PWD Nilanga, work of Improvement and Construction of Major Bridge on Nitur Shirol Helamb to SH-238 Road Mdr-43 Km 12/500 Nilanga, Latur was not completed within stipulated period of 24 months | Data of PWD works was accessed through BEAMS → MIS → PWD Works → PWD Capital Works Report. After entering the PWD Division details and selecting Show Report, were checked. The completion date was then calculated from Date of work order and original time limit and then date of RA bill payment was cross checked to determine whether the work was delayed. | If Date of RA bill payment was beyond the stipulated date of completion (calculated from Date of work order and original time limit) then there is red flag for non-imposition of penalties for delayed execution |
| 6 | Non renewal of Insurance Policy/BG on ongoing works As per the tender conditions, the Insurance Policy and Bank Guarantee must be submitted and renewed in a timely manner till completion of work and upon expiry of their validity period | BEAMS-MIS- PWD Capital Works- Work details | In PWD Nilanga, work of Improvement and Construction of Major Bridge on Nitur Shirol Helamb to SH-238 Road Mdr-43 Km 12/500 Nilanga, Latur was not completed within stipulated period of 24 months | Data of PWD works was accessed through BEAMS → MIS → PWD Works → PWD Capital Works Report. After entering the PWD Division details and selecting Show Report, individual works—particularly those with high contract values—were checked. The completion period was verified to determine whether the work was completed within the prescribed period or delayed. | If Date of RA bill payment was beyond the stipulated date of completion (calculated from Date of work order and original time limit) then there is red flag for Lapse of Insurance policy and Bank Guarantee |
| 7 | Splitting of work to avoid sanction of higher authority —Chief Engineer has the power to accept tender having cost more than Rs. 2.50 Crore & up to Rs. 15.00 Crore, whereas tender having cost more than Rs. 15 Crore are to be accepted at Government level. | BEAMS MIS reports- PWD Capital Works | In PWD Arvi, works of Improvement and two years maintenance to Morshi Ashti Thar Pardi Nara Karanja Road SH-292 in Km218/00 to 228/00 Taluka Ashti Dist Wardha, and Improvement and two years maintenance to Morshi Ashti Thar Pardi Nara Karanja SH-292 in Km 228/00 To238/00 Taluka Ashti Dist Wardha for cost of ₹ 9.99 crore and ₹ 9.21 crore was accepted by CE. As the works were in adjacent lengths, it seems to split up to avoid sanction from Government. | BEAMS -> MIS -> PWD Works -> PWD Capital Works Report-> Fields - Name of the work-Amount of Technical Sanction | If similar Name of works in the PWD Capital works under PWD works in MIS is found to have adjacent length on same road with huge amount of technical sanction cost (say more than ₹ 1 crore), then there is red flag for split up to avoid sanction of higher authority. |
| 8 | Irregular payments on Hand Receipt- MPW Manual provisions prescribe that huge payment for regular work (for which forms are prescribed) on Hand Receipt should generally be avoided. | Extract of Cash book (Form 10) from AMS | PWD Nagbhid- Cash book (Form 10) for Month of March 2025- Voucher no. 439 dated 27.03.2025, amount of ₹ 2.37 crore was paid vide HR although work was under HAM and there was prescribed bill format for payments in that | Cash book (Form 10) of any month AMS (pdf of excel)- To search for Huge Amount (say more than 10 lakh) paid on Hand Receipt | If any payment in Cash Book (Form 10) of any month shows any payment in excess of ₹ 10.00 lakh as “paid vide Hand Receipt” or “paid vide H.R.” or “Paid vide HR then it is a red flag for irregular payment |
| 9 | Irregular payment without proper classification- Huge payment in cash book but Classification (Head of accounts) not shown in the relevant column | Cash Book (Form 10 from AMS)- | In PWD Arvi, Payment of Rs.850.97 lakh to Sharda Construction without any detailed classification in the cash book vide Voucher No. 95 dated 28.08.2025 | To search for huge payment (say more than 10 lakh) with no classification of heads in the classification column | If any payment in Cash Book (Form 10) of any month shows any payment in excess of ₹ 10.00 lakh without any entry of Major Head in the classification column then it is a red flag for irregular payment without proper classification |